## Gantt Chart
AI-Lingo ¦ Project Gantt Chart
Project period: 08 Oct 2026 – 04 Dec 2026 ¦ Team size: 5 Flutter developers
Planning draft: adjust task dates and owners to match the team's final responsibilities.
ID | Task | Workstream | Start Date | End Date | Duration (days) | Timeline (daily)
Calendar | time axis 2026-10-08 to 2026-12-04
1 | Project Proposal & Requirements | Project Management | 2026-10-08 | 2026-10-13 | 6 | bar: 2026-10-08 to 2026-10-13; 2026-10-24; 2026-11-28
2 | Literature Review & Research | Research | 2026-10-10 | 2026-10-16 | 7 | bar: 2026-10-10 to 2026-10-18; 2026-10-24; 2026-11-28
3 | Project Planning | Project Management | 2026-10-12 | 2026-10-16 | 5 | bar: 2026-10-10 to 2026-10-18; 2026-10-24; 2026-11-28
4 | UI/UX Design | Design | 2026-10-14 | 2026-10-22 | 9 | bar: 2026-10-14 to 2026-10-22; 2026-10-24; 2026-11-28
5 | System Architecture & Database Design | Architecture | 2026-10-17 | 2026-10-24 | 8 | bar: 2026-10-17 to 2026-10-24; 2026-11-28
6 | Flutter Project Setup | Flutter | 2026-10-20 | 2026-10-24 | 5 | bar: 2026-10-20 to 2026-10-24; 2026-11-28
7 | Core UI Development | Flutter | 2026-10-23 | 2026-11-04 | 13 | bar: 2026-10-23 to 2026-11-04; 2026-11-28
8 | Authentication & User Profile | Flutter | 2026-10-29 | 2026-11-07 | 10 | bar: 2026-10-24; 2026-10-29 to 2026-11-08; 2026-11-28
9 | AI Conversation Feature | AI Integration | 2026-11-02 | 2026-11-12 | 11 | bar: 2026-10-24; 2026-10-31 to 2026-11-12; 2026-11-28
10 | Learning & Progress Tracking | Flutter | 2026-11-06 | 2026-11-15 | 10 | bar: 2026-10-24; 2026-11-06 to 2026-11-15; 2026-11-28
11 | Backend & Data Integration | Integration | 2026-11-08 | 2026-11-18 | 11 | bar: 2026-10-24; 2026-11-07 to 2026-11-18; 2026-11-28
12 | Feature Integration | Integration | 2026-11-16 | 2026-11-21 | 6 | bar: 2026-10-24; 2026-11-14 to 2026-11-22; 2026-11-28
13 | Testing & Bug Fixing | QA | 2026-11-20 | 2026-11-28 | 9 | bar: 2026-10-24; 2026-11-20 to 2026-11-28
14 | Documentation & Report | Documentation | 2026-11-22 | 2026-12-01 | 10 | bar: 2026-10-24; 2026-11-21 to 2026-12-01
15 | Final Review & Submission | Delivery | 2026-12-02 | 2026-12-04 | 3 | bar: 2026-10-24; 2026-11-28; 2026-12-02 to 2026-12-04
Legend
Blue bar | Flutter / AI feature work
Teal bar | Planning, research, integration, QA, documentation
Weekend | Weekend background in timeline

## Task Details
AI-Lingo ¦ Task Schedule
Edit the start/end dates, status, progress, and notes as the project evolves.
ID | Task | Workstream | Start Date | End Date | Duration (days) | Status | Progress | Task Notes
1 | Project Proposal & Requirements | Project Management | 2026-10-08 | 2026-10-13 | 6 | Not started | 0% | Define idea, problem statement, solution, objectives, scope, and requirements.
2 | Literature Review & Research | Research | 2026-10-10 | 2026-10-16 | 7 | Not started | 0% | Review related English-learning and AI conversation apps; summarize findings.
3 | Project Planning | Project Management | 2026-10-12 | 2026-10-16 | 5 | Not started | 0% | Confirm work breakdown, responsibilities, milestones, and schedule.
4 | UI/UX Design | Design | 2026-10-14 | 2026-10-22 | 9 | Not started | 0% | Prepare user flows, wireframes, and main screen designs.
5 | System Architecture & Database Design | Architecture | 2026-10-17 | 2026-10-24 | 8 | Not started | 0% | Plan app architecture, data models, and storage/API structure.
6 | Flutter Project Setup | Flutter | 2026-10-20 | 2026-10-24 | 5 | Not started | 0% | Set up project structure, dependencies, navigation, and shared conventions.
7 | Core UI Development | Flutter | 2026-10-23 | 2026-11-04 | 13 | Not started | 0% | Implement the main screens and reusable UI components.
8 | Authentication & User Profile | Flutter | 2026-10-29 | 2026-11-07 | 10 | Not started | 0% | Implement sign-in/sign-up flow and profile screens.
9 | AI Conversation Feature | AI Integration | 2026-11-02 | 2026-11-12 | 11 | Not started | 0% | Build the AI-powered English conversation experience.
10 | Learning & Progress Tracking | Flutter | 2026-11-06 | 2026-11-15 | 10 | Not started | 0% | Implement learning activities and progress tracking.
11 | Backend & Data Integration | Integration | 2026-11-08 | 2026-11-18 | 11 | Not started | 0% | Connect app features to required APIs/services and persist data.
12 | Feature Integration | Integration | 2026-11-16 | 2026-11-21 | 6 | Not started | 0% | Integrate features and resolve cross-feature issues.
13 | Testing & Bug Fixing | QA | 2026-11-20 | 2026-11-28 | 9 | Not started | 0% | Test user flows, fix bugs, and check stability.
14 | Documentation & Report | Documentation | 2026-11-22 | 2026-12-01 | 10 | Not started | 0% | Complete technical documentation and project report.
15 | Final Review & Submission | Delivery | 2026-12-02 | 2026-12-04 | 3 | Not started | 0% | Final checks, presentation preparation, and submission.

## Milestones
AI-Lingo ¦ Project Milestones
Milestone | Target Date | Success Criteria | Status
Proposal & initial planning complete | 2026-10-16 | Proposal, requirements, and project plan reviewed | Completed
UI/UX design complete | 2026-10-22 | Main user flows and screen designs approved | Not started
Architecture & setup complete | 2026-10-24 | Architecture and Flutter project foundation ready | Not started
Core UI complete | 2026-11-04 | Main screens and reusable components implemented | Not started
AI conversation feature ready | 2026-11-12 | Conversation flow works in the app | Not started
Features integrated | 2026-11-21 | Core features connected and usable together | Not started
Testing complete | 2026-11-28 | Major bugs resolved and key flows tested | Not started
Final submission | 2026-12-04 | Final report and deliverables submitted | Not started

## Deliverables
ID | Deliverable | Description | Due Date | Responsible | Status
D1 | Project Proposal | Project idea, problem, solution, objectives and scope | 2026-10-13 | All Members | Done
D2 | Requirements Document | Functional and non-functional requirements | 2026-10-13 | Yahia Yasser | Done
D3 | UI/UX Design | Figma screens and user flows | 2026-10-22 | All Members | Not started
D4 | Flutter Application | Main application screens and features | 2026-11-21 | All Members | Not started
D5 | AI Integration | AI conversation functionality | 2026-11-21 | Tasneem Elsayed | Not started
D7 | Testing Report | Test cases and testing results | 2026-11-28 | Nour Shaaban | Not started
D8 | Final Presentation | Presentation and demo preparation | 2026-12-03 | All Members | Not started

## Resource Allocation
Member | Role | Responsibilities | Assigned Tasks
Tasneem Elsayed Raneem A.shawky Toqa Shamaa Nour Shaaban Yahia Yasser | Project Manager | Planning and progress tracking | Proposal, Planning, Documentation
Tasneem Elsayed Raneem A.shawky Toqa Shamaa Nour Shaaban Yahia Yasser | UI/UX Designer Flutter Developer | UI design & App development and state management | UI/UX , Core UI, Authentication
Tasneem Elsayed | AI Engineer | AI model/API integration | AI Conversation
Nour Shaaban Toqa Shamaa | Backend & Testing | Data integration and testing | Backend, Testing
Resource | Purpose
Flutter & Dart | Mobile application development
Figma | UI/UX design
GitHub | Version control and collaboration
Database / Backend | Data storage and integration
AI API / Model | AI conversation feature
Testing Devices | Application testing